## FORMAT OF ERECTION
II.Illustration of Price Schedule (Erection of Plant):
Supply, Installation, Testing and Commissioning of LT Aerial Bunched Cable With Its Accessories In Part of Kachchh District (Anjar Circle) in PGVCL under Revamped Reforms-Based and Results-Linked, Distribution Sector Scheme (Package-2).
(Schedule of rates and Prices)
Ex-Works Erection of Materials
Bidder's Name & Address: M/s SES & PPCW(JV),Modasa
Circle - ANJAR Division - ANJAR Sub-Division - ANJAR CITY Feeder code - 74120 Feeder Name - AJEPAR URBAN
|  | LOA |  |  |  | SURVEY
Sr. No. | Description of Goods | Unit | Quantity | Unit Exworks price in Rs. | Total Price per line item in Rs. | Quantity | Unit Exworks price in Rs. | Total Price per line item in Rs. | Remarks
1 | Survey, route alignment and pole spotting, Tree cutting and compensation, preparation of survey report and uploading in the web portal after approval of Project Manager. | Km | 1599 | 740.4
2 | Erection Of PSC Poles of 8 Mt./200 Kg including excavation of pit and refilling of earth, fixing of Cross arms, Top Fitting Clamps, Anti-Climbing Devices with Barbed wire, Insulators, etc. complete and painting of fabricated materials used on the poles and numbering with cost of paint as per Standard Specification. | No. | 3197 | 740.4 |  | 19
3 | Installation of Guy Set with preformed fitting, Anchor Rod - 1 No, Turn Buckel – 1 No, Eye Bolt – 1 No, Stay wire - 7/12 - 2.5 kg, LT Guy Insulator – 1 No, Guy Clamp - 1 Pair, Nut - Bolt (65x16 mm)-2 Nos. - as per Requirement etc. as per approved drawing. | Set | 3997 | 419.56 |  | 19
4 | Installation of Coil type Earthing consist of (a) 8 SWG GI wire for earthing coil- 1.7 Kg (b) Rigid PVC Pipe 20mm dia ( 1.5 Mtr) - 1No (C) Earthing Bolt- 1 No (d) GI Wire No. 8 From Pole Top to Earthing Coil- 1.06 Kg including cost of Coal Salt etc. (20 KG SALT + 20 KG COAL) using existing earthing pit as per approved drawings, technical specifications and scope of work by removing and creaditing old earthing coil/plate and earth wire to the concerned Division store through Subdivision. | Set | 7994 | 582.45 |  | 152
5.01 | AERIAL BUNCHED XLPE CABLE 1.1 KV 3C X 50 SQ.MM+1Cx25 SQ. MM.+1x35 SQ. MM. including special accessories for AB cable as specified in Scope of work and as per approved drawings, technical specifications. | Km | 902 | 20731.2 |  | 21.21
5.02 | AERIAL BUNCHED XLPE CABLE 1.1 KV 1Cx 35 SQ MM + 1CX16 SQ MM + 25 SQ MM including special accessories for AB cable as specified in Scope of work and as per approved drawings, technical specifications. | Km | 697 | 10464.32 |  | 0.03
6 | Removal / Dismentling of ex. LT Line conductor/ Deteriorated AB cable (All Size), Removal Of Hardware and Crediting to store including transportation as REQUIRED and DIRECTED BY ENGINEERIN- CHARGE. | Km | 1599 | 3731.62
7.01 | 1-ph Pole mounted service connection box for LT connections (8 connections) | No | 7194 | 246.8 |  | 114
7.02 | 3-ph Pole mounted service connection box for LT connections (4 connections) | No | 799 | 345.52 |  | 29
Total Cost Exculding GST
Applicable GST
Grand Total Including GST